## Sheet1
Date | Topics discussed | To do
9th November | Discussion regarding thesis proposal | First draft of the outline of the report
| priliminary discussion on the methods, type of visualizations and evaluation metrics | Read papers on evaluation metrics
Rough time table was set
23rd November | proposed outline of the report (corrections were suggested) | Update the report focusing more on evaluation metrics
Read on association mining and critiquing techniques
7th December | Revised structure of the report | revised overview of literature survey
| Association mining | try to replicate the implementation in the exisiting work
| Critiquing | (From now on meeting every thursday 1-1.30 )
About how to extract user's profiles
(Discussed about leaves, github repository and the presentation to epsilon group)